## Sheet1
Day | DATE | Activity(programming) | Written- all write relavent design and testing I did
Monday | 2016-01-04 | Write Timetable and continue work on GUI
Tuesday | 2016-01-05 | Continue GUI
Wednesday | 2016-01-06 | GUI
Thursday | 2016-01-07 | Create Database
Friday | 2016-01-08
Saturday | 2016-01-09
Sunday | 2016-01-10
Monday | 2016-01-11 | Inplement DataBase into Program | Test this feature
Tuesday | 2016-01-12 | Create flashcard
Wednesday | 2016-01-13 | Finish flashcard , Create Inteface To add cards
Thursday | 2016-01-14 | finish Add interface and begin flashcard collection from db
Friday | 2016-01-15
Saturday | 2016-01-16
Sunday | 2016-01-17
Monday | 2016-01-18 | flashcard collection from db
Tuesday | 2016-01-19 | create card viewing interface
Wednesday | 2016-01-20 | finish card viewing interface
Thursday | 2016-01-21 | Write a list of statistics to be tracked , and add these to interface and db
Friday | 2016-01-22
Saturday | 2016-01-23
Sunday | 2016-01-24
Monday | 2016-01-25 | Enable stats to be dynamically updated | test this
Tuesday | 2016-01-26 | Create algorthym to collect correct card cards
Wednesday | 2016-01-27 | continue above
Thursday | 2016-01-28 | Create card generating alogorthing
Friday | 2016-01-29
Saturday | 2016-01-30
Sunday | 2016-01-31
Monday | 2016-02-01 | create base for graph questions
Tuesday | 2016-02-02 | finish above
Wednesday | 2016-02-03 | create base for differentiation questions
Thursday | 2016-02-04 | and integration
Friday | 2016-02-05
Saturday | 2016-02-06
Sunday | 2016-02-07
Monday | 2016-02-08 | Finish graph section
Tuesday | 2016-02-09
Wednesday | 2016-02-10
Thursday | 2016-02-11
Friday | 2016-02-12
Saturday | 2016-02-13
Sunday | 2016-02-14
Monday | 2016-02-15 | Algorth for basic differentiation and integration
Tuesday | 2016-02-16
Wednesday | 2016-02-17
Thursday | 2016-02-18
Friday | 2016-02-19
Saturday | 2016-02-20
Sunday | 2016-02-21
Monday | 2016-02-22 | Above | finish design and check all other sections are up to date
Tuesday | 2016-02-23
Wednesday | 2016-02-24 | Implement graph and calculus to own section
Thursday | 2016-02-25 | Create timed game
Friday | 2016-02-26 |  | user manual
Saturday | 2016-02-27
Sunday | 2016-02-28
Monday | 2016-02-29 | User feedback | system maintenace and appraisal
Tuesday | 2016-03-01
Wednesday | 2016-03-02
Thursday | 2016-03-03
Friday | 2016-03-04
Saturday | 2016-03-05
Sunday | 2016-03-06
Monday | 2016-03-07 | Improve on feedback
Tuesday | 2016-03-08
Wednesday | 2016-03-09
Thursday | 2016-03-10
Friday | 2016-03-11